## Executive Summary (What must be true for success)

- Authoritative Identity & PKI are wired into the platform (IdP + RBAC + service account model + certificate issuance/rotation for mTLS).

- Tenant isolation is enforceable end-to-end (per-tenant VLZ addressing, BGP policy, DNS views, and L7 proxy choke points).

- Automation is the system of record (API-first workflows, Terraform modules, golden templates for IPsec/proxy/DNS).

- Observability is multi-layer and per-tenant (DNS, proxies, tunnels, BGP, and app telemetry flow into SIEM with consistent IDs).

- Governance is embedded into the request flow (data classification, compliance tags, approvals, and auditable decisions).

These five threads form your critical path; slippage in any one of them will stall pilot or create unmanageable risk at scale.

## A. Critical-Path Dependencies (Day-0 to start a POC)

### 1) Identity, Access, and PKI

- Dependencies

  - IdP federation (SSO) for the portal + RBAC roles (requestor, approver, operator, auditor).

  - Service principals/app registrations for automation pipelines (least-privilege scopes).

  - PKI integration: issuing CAs, profiles, mTLS server & client certs, CRLs/OCSP, automated renewal.

- Risks

  - Non-existent or ad-hoc RBAC → shadow approvals; stale certs → outages.

- Mitigations

  - Define an Access Control Matrix and bind to IdP groups.

  - Build cert lifecycle runbooks + auto-rotation (≤ 90-day certs).

### 2) Network Underlay & Tunnel Anchors

- Dependencies

  - HA IPsec termination points (regionally redundant), VTI interfaces, per-tenant addressing, and BGP policies (inbound route filters, max-prefix, communities).

  - Standard crypto profiles (IKEv2, DH groups, ciphers) and reference configs for target peer platforms (Palo Alto, Cisco, Fortinet, etc.).

- Risks

  - Crypto/profile mismatch → tunnel flaps; permissive BGP → route leaks; shared CIDRs → tenant collisions.

- Mitigations

  - Publish golden IPsec bundles; enforce prefix-lists and as-path filters; reserve per-tenant RFC1918 pools.

### 3) DNS as a Control Plane

- Dependencies

  - Per-tenant split-horizon views, conditional forwarding rules, and rewrite from enterprise FQDNs → tenant proxy VIPs.

  - Authoritative naming conventions for tenants, services, and environments.

- Risks

  - Incorrect DNS rewrite/TTL → session pinning or bypass; shared records → cross-tenant bleed.

- Mitigations

  - Scoped zones per tenant; low TTL during pilot; DNS change guardrails in CI.

### 4) L7 Service Proxies & Policy Packs

- Dependencies

  - Hardened proxy stacks for Web, API, SFTP/SSH, VDI, Collaboration with policy packs (TLS params, headers/paths, auth, rate limits, file size caps).

- Risks

  - Weak defaults → inconsistent enforcement; no per-pattern baselines → prolonged onboarding.

- Mitigations

  - Create pattern blueprints with “must/should/may” controls; pre-QA them in a staging VLZ.

### 5) Observability, Logging, and Forensics

- Dependencies

  - Per-tenant logging for DNS, proxy, tunnel/BGP, and access decisions; common correlation IDs; exports to SIEM/metrics.

- Risks

  - Blind spots across layers → slow triage; mixed tenant logs → audit failures.

- Mitigations

  - Enforce structured logging (tenant_id, app_id, 3pBID, env); create field-level contracts and dashboards before pilot.

### 6) Workflow, API, and IaC Automation

- Dependencies

  - Portal/API for intake → validation → approvals → provisioning; Terraform modules for repeatability; CI/CD with change windows.

- Risks

  - Manual builds → drift; pipeline creds sprawl → secrets risk.

- Mitigations

  - One authoritative pipeline; module versioning; secret brokers (Vault/KMS) with short-lived tokens.

### 7) Governance, Risk, Compliance (GRC) Embedding

- Dependencies

  - Data classification & regulatory flags in the request form (PHI/PII, residency, retention).

  - Approval chains that vary by risk tier; attestation capture.

- Risks

  - Out-of-band approvals → gaps; audit findings for missing attestations.

- Mitigations

  - Bake policy “gates” into the portal; require attestation artifacts to proceed.

## B. Track-By-Track Dependencies, Risks, Mitigations

### Track 1 — Identity & PKI

- Dependencies

  - IdP groups mapped to RBAC roles; SCIM/Group APIs for lifecycle; PKI profiles for mTLS (server/client); automated renewal hooks.

- Risks

  - Orphaned accounts; cert expiry; inconsistent client-auth on proxies.

- Mitigations

  - Joiner/Mover/Leaver automation; cert grace windows + auto-renew tests; mTLS pinning policies per pattern.

### Track 2 — Network & Routing

- Dependencies

  - Tenant IP plan; VRF/namespace per tenant; BFD for VTI stability (if supported); rate-limit & DoS guards at anchors.

- Risks

  - Address exhaustion; asymmetric paths; noisy neighbor on anchors.

- Mitigations

  - Reserve /28–/27 pools per tenant; path health SLOs; per-tenant policing and connection quotas.

### Track 3 — DNS & Namespace Management

- Dependencies

  - Delegation model; authoritative VLZ zones; DNSSEC (if required); audit of wildcard usage.

- Risks

  - Cache poisoning vectors; too-broad wildcards.

- Mitigations

  - Minimize wildcards; implement DNS change reviews; conditional forwarding testing with 3rd-party resolvers.

### Track 4 — L7 Proxies (Web/API/VDI/SFTP/Collab)

- Dependencies

  - Hardened baseline (TLS 1.2+/1.3, cipher policy, HSTS); method/path allow-lists; request size and concurrency limits; mTLS/JWT validators; SSH proxy with session logging.

- Risks

  - Bypass via direct IPs; header smuggling; SSH key sprawl.

- Mitigations

  - Force FQDN-only access; header canonicalization; central key store and short-lived certs for SSH key-to-user mapping.

### Track 5 — Observability & SIEM

- Dependencies

  - Normalized schemas; per-tenant indices; dashboards for: tunnel health, DNS NXDOMAIN spikes, proxy 4xx/5xx, throttling events.

- Risks

  - Noisy logs; lack of cross-layer correlation.

- Mitigations

  - Sampling policies; global correlation ID carried in DNS→Proxy→App; SLOs with alert thresholds (e.g., tunnel availability ≥ 99.9%).

### Track 6 — Automation & Pipelines

- Dependencies

  - Versioned Terraform modules (ipsec_vti, bgp_peer, dns_view, proxy_policy); environment promotion (dev→test→prod); canary deployments.

- Risks

  - Template drift; broken rollbacks.

- Mitigations

  - Module registries, semantic versioning, one-click rollback with state snapshots.

### Track 7 — Security Testing & Assurance

- Dependencies

  - Pre-prod pen tests per pattern; negative tests (e.g., mTLS missing, invalid scopes, DNS direct-to-origin attempts); SSH session recording validation; DLP hooks for SFTP if required.

- Risks

  - Control gaps only found in production; forensic gaps.

- Mitigations

  - Pattern certification gates; chaos tests for tunnel failover; red-team exercises on a sacrificial tenant.

### Track 8 — Data Governance & Legal

- Dependencies

  - Data classification in the form; data processing agreements (DPAs) by region; retention settings for logs & transfers; right-to-audit clauses for partners.

- Risks

  - Residency violations; over-retention.

- Mitigations

  - Policy-driven retention (e.g., PHI = 7 years logs, vendor data = 1 year); auto-tagging and enforcement.

### Track 9 — Vendor Management & Runbook Readiness

- Dependencies

  - Onboarding reference kits for partner firewalls/routers; support SLAs; escalation paths; UAT playbooks for each pattern.

- Risks

  - Repeated first-time issues; long MTTI due to unclear ownership.

- Mitigations

  - Publish turn-key bundles; L1/L2 runbooks; RACI for outages (who pages whom, for what).

### Track 10 — Financials & Capacity

- Dependencies

  - Anchor capacity modeling (tunnels, CPS, bandwidth, TLS TPS); logging/ingest costs by tenant; OPEX for 2026 growth curve.

- Risks

  - Anchor saturation; SIEM cost spikes.

- Mitigations

  - Per-tenant quotas, autoscaling for proxies, budget guardrails with usage alerts.

### Track 11 — Change, Comms, and Training

- Dependencies

  - Enablement for app teams; concise how-to videos; comms plan for cutovers; change calendar integration.

- Risks

  - Shadow paths kept alive; misconfig by requestors.

- Mitigations

  - Decommission SLAs for old paths; “shift-left” validation in the form; mandatory sandbox dry-run.

## C. Phased Readiness & Exit Criteria

### POC Entry (what must be ready)

- IdP SSO + RBAC roles; PKI integrated; at least two service patterns certified (e.g., Web/API).

- Anchor pair live with test tenants; per-tenant DNS view working; SIEM dashboards online.

- Terraform modules for ipsec_vti, dns_view, proxy_policy are versioned and promoted in CI.

### POC Exit (to move to Pilot)

- Demonstrate mTLS Web/API + SFTP with session logging + VDI in at least 3 tenants.

- Show full audit trail from request → approval → provision → logs.

- Hit SLOs: tunnel availability ≥ 99.9%, proxy p95 latency thresholds met, error budgets intact.

### Pilot Exit (to scale)

- Throughput test with ≥ 25 tenants, 4 patterns each; no cross-tenant leakage; cost telemetry stable.

- Runbooks executed in live incident sim (tunnel flap, DNS error, cert expiry) with acceptable MTTR.

## D. Dependency Checklist (Copy/Paste into your tracker)

[ ] IdP SSO + RBAC groups mapped to roles; SCIM group sync in place

[ ] PKI: issuing CA, profiles, automation hooks for mTLS (Web/API), SSH key/cert flows

[ ] HA tunnel anchors online; golden IPsec bundles for top vendor platforms

[ ] Per-tenant IP plan, VRF/namespace, BGP policies (in/out filters, max-prefix)

[ ] DNS: split-horizon views, conditional forwarding, rewrite rules, naming standards

[ ] Certified policy packs for Web/API/VDI/SFTP/Collab with baseline TLS & auth

[ ] Structured logging schema (tenant_id, app_id, 3pBID, env, corr_id); SIEM pipelines & dashboards

[ ] Terraform modules (ipsec_vti, bgp_peer, dns_view, proxy_policy) versioned; CI/CD wired

[ ] Portal form validations (data classification, region, retention, auth type) + approval chains

[ ] Pen test plan per pattern + negative test suite; chaos/failover tests

[ ] Vendor onboarding kits; L1/L2 runbooks; escalation matrix and SLAs

[ ] Capacity model & budgets; per-tenant quotas; autoscaling thresholds

[ ] Training & comms plan; decommission SLAs for legacy paths

## E. Recommended Sequencing (90-Day Plan)

- Days 0–30 (Foundations): IdP/RBAC, PKI hooks, anchors online, per-tenant DNS views, Terraform modules ready; certify Web/API pattern.

- Days 31–60 (Broaden Controls): Add SFTP/SSH with session logging; VDI proxy; full SIEM dashboards; negative test suite; first 5 partner pilots.

- Days 61–90 (Resilience & Scale): Chaos tests (anchor failover, cert expiry, DNS break); cost telemetry & quotas; runbook drills; 20–25 tenants live.