## Slide 1
Our Understanding
Solution Approach & Architecture
Team Summary / Metrics
Price
Key Assumptions
CVS Health 3rd Party Landing Zone Portal
This initiative is a strategic modernization of CVS’s third-party connectivity model, delivering a secure, automated, and self-service 3PLZ platform. The solution will replace manual, bespoke integrations with a standardized, policy-driven approach that enforces tenant isolation, least-privilege access, and identity-based controls by default. Through a simple portal and API, application teams will onboard partners without network expertise while maintaining compliance and reducing operational overhead. The program’s success is defined by delivering a production-ready platform within one year, onboarding up to five initial partners, and establishing a scalable foundation capable of supporting enterprise-wide third-party connectivity at scale.
CVS will provide executive sponsorship and timely decision-making
A primary vendor will be selected and fully engaged for the duration of the program
Existing CVS IAM, PKI, and SIEM platforms are available for integration
Initial scope is limited to defined service patterns and up to five partner onboardings
The platform will prioritize automation and self-service over custom integrations
Security and compliance requirements are approved during design and remain stable through delivery
Solution Owner | US
Application Architect | US
Sr. AppDev Principal Engineer | India
Sr. UI Designer | India (100% for 2 months)
3 Engineers *
Sr. QA Engineer *
Estimated Cost: $2,032,000.00
(*) Pending refinement of scope as the project matures
(*) Resources assignment and refinement will adjust as scope as the project matures
All Resources shown are at 100% allocation unless otherwise stated
Design and Alignment
Platform Build & MVP
Pilot Onboarding
12 Month breakdown of Activities and Outcomes by Phase
Months 1–2
Define portal workflows, RBAC, and approval gates
Establish governance, roles, and success metrics
Finalize reference architecture, tenant/VLZ model, and service patterns
Align security, compliance, and operating model
Months 3–6
Build portal, APIs, and automation/orchestration layer
Implement tenant/VLZ creation and IPsec “VPN to nowhere”
Deliver DNS rewriting and initial service proxies (Web/API and generic TCP)
Enable logging, monitoring, and SIEM integration
Activities
Outcomes
Approved end-to-end architecture and delivery plan
Clear service catalog and onboarding workflows
Security and compliance requirements locked
Readiness to begin platform build
Functional MVP platform in a production-like environment
Automated, self-service tenant and tunnel provisioning
First service patterns available for consumption
Operational visibility and auditability established
Months 7-9
Onboard first 1–2 pilot partners using self-service workflows
Execute functional, security, and failover testing
Refine portal UX, automation, and dashboards
Develop and validate runbooks and support processes
Successful onboarding of initial pilot partners
Validated security, resilience, and operational model
Refined platform based on real-world usage
Operations team ready to support production use
Scale Pilot & Transition
Months 9-12
Onboard additional partners (up to 5 total) using standardized patterns
Validate repeatability, onboarding SLAs, and minimal operational touch
Complete production acceptance and security sign-off
Define Year-2 roadmap and scale strategy
Up to five partners live on the platform
Proven, repeatable self-service onboarding model
Reduced manual effort and operational risk
Scalable foundation ready for enterprise-wide expansion